## Product Description
Product Description of hiCreo
ACLC is developing a new product (hiCreo). hiCreo is a fully hosted software-as-a-service (SaaS) that empowers organizations to deliver training anytime, anywhere. hiCreo is an eLearning design and development tool, enabling non-experts to build modules and incorporate interactive components into eLearning or mLearning.

## Audience
Audience
The user of the product and the audience for the White Paper may be two different audiences, and I must write for both.
Product User:
· Instructional Systems Designers (ISDs)
· Subject Matter Experts (SMEs)
· Trainers/Instructors
Product User Needs:
· Need to create eLearning content without a development team or graphic designers at their disposal
How the Product Meets User Needs:
· hiCreo has built-in eLearning templates, which allows non-expert users to create eLearning content.
Project Audience:
· Government customer (Contracting Office)
Project Audience Needs:
· Provide quality, cost-efficient services to the Government
How the Project Meets Audience Needs:
· The White Paper meets the audience needs because it combines research with a value proposition and problem solution. The audience (Government) is also familiar and comfortable with a White Paper product.
Most likely, the deliverable (White Paper) would reach both audiences, the end users and the buyers. The Contracting Office will often solicit SMEs to help in the evaluation of proposals or products for Government use. While the SMEs (who represent the end users) will understand basic concepts, the Contracting Office will not. Therefore, the White Paper will need to include some basic introductory explanation of the technology.

## Doc Products
Documentation Products
White Paper
Headline
Executive Summary
Intro: state the problem white paper solves (consequences for not taking action); summarize key areas of white paper; explain benefits of reading white paper (what will the reader be equipped to do after reading what we have to say?)
Subheadings
Sidebars
Conclusion/Call to Action

## Dependencies
Dependencies | Risk Mitigation
If my project is to succeed, I'm dependent on other large opportunities/proposals not starting until post-31 Jan. This will give me enough time to do the intensive research/information gathering needed to drive all the subsequent writing/content. | If a large opportunity or proposal drops pre-31 Jan., I will accelerate my schedule. Rather than giving roughly a full week to each color stage (Pink, Red, Gold, White), I will compress it to 3-4 business days.
If my project is to succeed, I need access to SMEs, reviewers, and survey and usability participants.
I need the help of the SME (Bradd Chi), the reviewers, the participants, and possibly graphic designers.
The biggest schedule checkpoints dependent on other stakeholders are the reviews, the survey results, and the usability testing results.

## Assumptions
Assumption
My largest assumption is that I and the people I have identified as resources for this project will have time during normal business hours to plan, research, write, and review for the hiCreo White Paper.

## Budget
Budget
Budget is my time and the (limited) time of my SME (Bradd Chi), reviewers (Bradd Chi, Kathryn Cox, Scott Phelps), editor (Arthur Berger), survey and usability test participants, and TBD graphics support.
Not formally paying/budgeting for this project, though many of the aforementioned people are ACLC employees and may be performing their tasks on-the-clock.

## Schedule
 | time axis 2019-01-21 to 2019-03-13
Victoria Berger | Tech. Writer | 2019-01-21: Send White Paper Development Schedule to Team; 2019-01-21: Gather Information; 2019-02-01: Develop Outline/Meet with SMEs; 2019-02-04: Write Pink Draft; 2019-02-08: Send Pink Draft out for Review (1200); 2019-02-11: Pink Draft Review Comments due (1200); 2019-02-12: Pink Recovery; 2019-02-13: Write Red Draft; 2019-02-20: Send Red Draft out for Review (1200); 2019-02-22: Red Draft Review comments due (1700); 2019-02-23: Red Recovery; 2019-02-25: Write Gold Draft; 2019-02-27: Send Gold Draft out for Review (1200); 2019-03-01: Gold Draft Review comments due (1700); 2019-03-02: Gold Recovery; 2019-03-03: Send to Editor; 2019-03-04: Apply Research on Usability Testing to Develop Usability Test for White Paper; 2019-03-05: Send Most Recent Version of White Paper to Participants and Conduct Usability Test; 2019-03-07: Incorporate Usability Test Findings into White Glove Version; Send White Glove out to Reviewers for comments (1700); 2019-03-11: White Glove review comments due (0900); Finalize; 2019-03-13: White Paper Presentation (1800)
Identify Graphics (Reach out to SMEs)
Bradd Chi | SME & Reviewer #1 | 2019-02-01: Meet with Tech. Writer to Go Over Outline; 2019-02-08: Review Pink Draft; 2019-02-11: Send Pink Review to Tech. Writer (1200); 2019-02-20: Review Red Draft; 2019-02-22: Send Red Review to Tech. Writer (1700); 2019-02-27: Review Gold Draft; 2019-03-01: Send Gold Review to Tech. Writer (1700); 2019-03-07: Review White Glove; 2019-03-11: Send White Glove Review to Tech. Writer (0900)
Kathryn Cox | Reviewer #2 | 2019-02-08: Review Pink Draft; 2019-02-11: Send Pink Review to Tech. Writer (1200); 2019-02-20: Review Red Draft; 2019-02-22: Send Red Review to Tech. Writer (1700); 2019-02-27: Review Gold Draft; 2019-03-01: Send Gold Review to Tech. Writer (1700); 2019-03-07: Review White Glove; 2019-03-11: Send White Glove Review to Tech. Writer (0900)
Scott Phelps | Reviewer #3 | 2019-02-08: Review Pink Draft; 2019-02-11: Send Pink Review to Tech. Writer (1200); 2019-02-20: Review Red Draft; 2019-02-22: Send Red Review to Tech. Writer (1700); 2019-02-27: Review Gold Draft; 2019-03-01: Send Gold Review to Tech. Writer (1700); 2019-03-07: Review White Glove; 2019-03-11: Send White Glove Review to Tech. Writer (0900)
Arthur Berger | Editor | 2019-03-03: Edit White Paper; 2019-03-05: Send Edited White Paper to Tech. Writer (0900)
ISDs, Trainers, Curriculum Developers | Survey Participants | 2019-01-25: Take hiCreo Survey; 2019-01-28: Return hiCreo Survey Results to Tech. Writer (1700)
ISDs, Trainers, Curriculum Developers | Usability Test Subjects | 2019-03-05: Take Usability Test; 2019-03-06: Send Usability Test Findings to Tech. Writer (1700)
TBD | Graphics

## WBS
Develop hiCreo White Paper
1.1 Architect/Design the Information | 1.2 Write a Doc Plan | 1.3 Gather Information | 1.4 Write Content | 1.5 Create Artwork | 1.6 Edit | 1.7 Review | 1.8 Index/SEO | 1.9 Test Usability | 1.10 Translate/Localize | 1.11 Publish Content
1.1.1 Identify "Ideal User Profile" | 1.2.1 Product Description | 1.3.1 Write Developer Survey to Gain Better Understanding of hiCreo | 1.4.1 Develop Outline | 1.5.1 Create Graphics (tables, flowcharts, org charts, simple graphs & pie charts) | 1.6.1 Send Document to Editor Post Gold Review and Pre White Glove (Arthur Berger) | 1.7.1 Distribute schedule to reviewers (End User: Kathryn Cox, ISD; Audience: Scott Phelps, Government/Contracting Acquisition Officer; Technical SME: Bradd Chi, Developer) | 1.8.1 Insert Index through "References" in Word | 1.9.1 Apply Research on Usability Testing (1.3.14) to Develop Usability Test for White Paper | 1.10.1 Not Applicable at this Time | 1.11.1 Do Print Test (in Color and B&W)
1.1.1.1 Meeting with SME (Bradd Chi) | 1.2.2 Audience | 1.3.1.1 Meet with SME (Bradd Chi) who Completes Developer Survey | 1.4.2 Meet with SMEs | 1.5.2 Access hiCreo for screengrabs | ***Note: As I have retained 3 reviewers for substantive/technical review, I view the editor as a copyeditor/proofreader and plan to utilize this position between the "Gold" and "White Glove" reviews. | ***Note: Reviewers have been selected to best represent the audience for this White Paper: an end user (ISD, trainer, curriculum developer); a Government Contracting Officer (t)he buyer); and a consultant SME (developer) |  | 1.9.2 Send White Glove Version (post Edit, pre White Glove Review) to Participants of User Survey and Conduct Usability Test |  | 1.11.2 Save as PDF
1.1.2 Determine Appropriate Medium (White Paper) | 1.2.3 Doc Products | 1.3.2 Research White Paper examples | 1.4.3 Identify Graphics | 1.5.3 Reach out to SMEs (graphic designers/developers) for Any Sophisticated Graphics, As Needed |  | 1.7.2 Pink Draft Review |  | 1.9.3 Incorporate Usability Test Findings into Document and Send for White Glove Review |  | ***Note: At this time, as the product is still in development, we are not publishing this White Paper or promoting it on our website. The White Paper's purpose is to send electronically (or as a printed copy in face-to-face meetings) to potential Government customers for future work opportunities/contracts.
1.1.3 Use ACLC Style Guide | 1.2.4 Tasks | 1.3.3 Research SaaS | 1.4.4 Write Pink Draft |  |  | 1.7.3 Red Draft Review
| 1.2.5 Dependencies | 1.3.4 Research Industry Data (Google Analytics; Alexa Topsites; Bureau of Labor Statistics; Small Business Administration; Pew Research) | 1.4.4.1 Perform Pink Draft Recovery (post Pink Draft Review) |  |  | 1.7.4 Gold Draft Review
| 1.2.6 Assumptions | 1.3.5 Research Cost Savings in eLearning | 1.4.5 Write Red Draft |  |  | 1.7.5 White Glove Review
| 1.2.7 Budget | 1.3.6 Research Writing to Two Audiences | 1.4.5.1 Perform Red Draft Recovery (post Red Draft Review)
| 1.2.8 Schedule | 1.3.7 Write User Survey and Send to Audience to Conduct Needs Assessment | 1.4.6 Write Gold Draft
| 1.2.9 WBS | 1.3.7.1 Audience consists of Instructional Systems Designers (ISDs), Trainers, Curriculum Developers, and Project Managers. | 1.4.6.1 Perform Gold Draft Recovery (post Gold Draft Review)
|  | 1.3.8 Explore the Survey Data | 1.4.6.2 Send to Editor
|  | 1.3.9 Organize Survey Data into User Personas | 1.4.7 Finalize (post White Glove)
1.3.10 Define Value Proposition
1.3.11 Create Customer Journey Map
1.3.12 Perform SWOT Analysis (Comparison of hiCreo to Adobe Products; Blackboard; eLearning Teams
1.3.13 Define Product Lifecycle
1.3.14 Research Usability Testing