## Schedule
|  | 2019-03-13 | 2019-03-14 | 2019-03-15 | 2019-03-16 | 2019-03-17 | 2019-03-18 | 2019-03-19 | 2019-03-20 | 2019-03-21 | 2019-03-22 | 2019-03-23 | 2019-03-24 | 2019-03-25 | 2019-03-26 | 2019-03-27 | 2019-03-28 | 2019-03-29 | 2019-03-30 | 2019-03-31 | 2019-04-01 | 2019-04-02 | 2019-04-03 | 2019-04-04 | 2019-04-05 | 2019-04-06 | 2019-04-07 | 2019-04-08 | 2019-04-09 | 2019-04-10 | 2019-04-11 | 2019-04-12
|  | RFP Release (R) | R+1 | R+2 | R+3 | R+4 | R+5 | R+6 | R+7 | R+8 | R+9 | R+10 | R+11 | R+12 | R+13 | Industry Day R+14 | R+15 | R+16 | R+17 | R+18 | R+19 | R+20 | R+21 | R+22 | R+23 | R+24 | R+25 | R+26 | R+27 | R+28 | R+29 | R+30
|  | RFP Release |  | Proposal/ Pink Team Kickoff | [9 empty] | Pink Recovery/ Red Team Kickoff | [7 empty] | Red Recovery/Gold Team Kickoff | [5 empty] | Gold Review |  | White Glove | Production | Proposal Due (1200)
Victoria Berger | Proposal Manager | 2019-03-13: Read RFP; Gather RFP Q's; create Compliance Matrix; Outline Volumes; 2019-03-14: Read RFP; Gather RFP Q's; create Compliance Matrix; Outline Volumes; 2019-03-15: Proposal Kickoff Conference Call 1100; Begin Pink Team Writing; 2019-03-19: SME Work Session 0900 ACLC Onsite or Call-in (Org Chart/Team Complemen/Labor Mix; Technical Understanding); 2019-03-20: Send out PPQs; Send out RFP Q's; 2019-03-22: Send Pink Draft (Vol2) to Reviewers (COB); Register for Industry Day; 2019-03-25: Pink Recovery/ Red Team Kickoff Conference Call (1100); 2019-03-27: SME Work Session 0900 ACLC Onsite or Call-in (Phase-In/Establish & Recruit/Fluctuating Workloads & Schedules); 2019-03-28: SME Work Session 0900 ACLC Onsite or Call-in (Org Chart/Team Complemen/Labor Mix; Technical Understanding); 2019-04-01: Send Red Draft (Vols2&3) to Reviewers (0900); 2019-04-02: Red Recovery/Gold Team KickoffConference Call (1100); 2019-04-05: Send Gold Draft (Vols 1,2,3) to Reviewers (0900); 2019-04-08: Perform Gold Recovery; Gold Review Conference Call (1100); 2019-04-10: White Glove Review (ACLC On-Site); 2019-04-11: Produce Proposal; 2019-04-12: Deliver Proposal (1200)
XYZ | Capture | 2019-03-13: Read RFP; gather Q's; 2019-03-20: Send out PPQs; 2019-03-22: Review Pink Draft (Vol2); 2019-03-25: Pink Draft (Vol2) Review Comments due to Victoria 0900; Pink Recover/ Red Team Kickoff Conference Call (1100); 2019-03-27: SME Work Session 0900 ACLC Onsite or Call-in (Phase-In/Establish & Recruit/Fluctuating Workloads & Schedules); 2019-03-28: SME Work Session 0900 ACLC Onsite or Call-in (Org Chart/Team Complemen/Labor Mix; Technical Understanding); 2019-04-01: Review Red Draft (Vols2&3); 2019-04-02: Red Draft (Vols2&3) Review Comments due to Victoria 0900; Red Recovery/ Gold Team Kickoff Conference Call (1100); 2019-04-05: Review Gold Draft (Vols1-3); 2019-04-08: Gold Review Comments due to Victoria 0900; Conference Call (1100); 2019-04-10: White Glove Review (ACLC On-Site)
XYZ | SME #1 | 2019-03-13: Read RFP; gather Q's; 2019-03-19: SME Work Session 0900 ACLC Onsite or Call-in (Org Chart/Team Complemen/Labor Mix; Technical Understanding); 2019-03-20: Send out PPQs; 2019-03-22: Review Pink Draft (Vol2); 2019-03-25: Pink Draft (Vol2) Review Comments due to Victoria 0900; Pink Recover/ Red Team Kickoff Conference Call (1100); 2019-03-28: SME Work Session 0900 ACLC Onsite or Call-in (Org Chart/Team Complemen/Labor Mix; Technical Understanding); 2019-04-01: Review Red Draft (Vols2&3); 2019-04-02: Red Draft (Vols2&3) Review Comments due to Victoria 0900; Red Recovery/ Gold Team Kickoff Conference Call (1100); 2019-04-05: Review Gold Draft (Vols1-3); 2019-04-08: Gold Review Comments due to Victoria 0900; Conference Call (1100)
XYZ | SME #2 | 2019-03-13: Read RFP; gather Q's; 2019-03-19: SME Work Session 0900 ACLC Onsite or Call-in (Org Chart/Team Complemen/Labor Mix; Technical Understanding); 2019-03-20: Send out PPQs; 2019-03-22: Review Pink Draft (Vol2); 2019-03-25: Pink Draft (Vol2) Review Comments due to Victoria 0900; Pink Recover/ Red Team Kickoff Conference Call (1100); 2019-03-28: SME Work Session 0900 ACLC Onsite or Call-in (Org Chart/Team Complemen/Labor Mix; Technical Understanding); 2019-04-01: Review Red Draft (Vols2&3); 2019-04-02: Red Draft (Vols2&3) Review Comments due to Victoria 0900; Red Recovery/ Gold Team Kickoff Conference Call (1100); 2019-04-05: Review Gold Draft (Vols1-3); 2019-04-08: Gold Review Comments due to Victoria 0900; Conference Call (1100); 2019-04-10: White Glove Review (ACLC On-Site)
XYZ | SME #3 | 2019-03-13: Read RFP; gather Q's; 2019-03-19: SME Work Session 0900 ACLC Onsite or Call-in (Org Chart/Team Complemen/Labor Mix; Technical Understanding); 2019-03-22: Review Pink Draft (Vol2); 2019-03-25: Pink Draft (Vol2) Review Comments due to Victoria 0900; Pink Recover/ Red Team Kickoff Conference Call (1100); 2019-03-28: SME Work Session 0900 ACLC Onsite or Call-in (Org Chart/Team Complemen/Labor Mix; Technical Understanding); 2019-04-01: Review Red Draft (Vols2&3); 2019-04-02: Red Draft (Vols2&3) Review Comments due to Victoria 0900; Red Recovery/ Gold Team Kickoff Conference Call (1100); 2019-04-05: Review Gold Draft (Vols1-3); 2019-04-08: Gold Review Comments due to Victoria 0900; Conference Call (1100)
XYZ | SME #4 | 2019-03-13: Read RFP; gather Q's; 2019-03-19: SME Work Session 0900 ACLC Onsite or Call-in (Org Chart/Team Complemen/Labor Mix; Technical Understanding); 2019-03-22: Review Pink Draft (Vol2); 2019-03-25: Pink Draft (Vol2) Review Comments due to Victoria 0900; Pink Recover/ Red Team Kickoff Conference Call (1100); 2019-03-28: SME Work Session 0900 ACLC Onsite or Call-in (Org Chart/Team Complemen/Labor Mix; Technical Understanding); 2019-04-01: Review Red Draft (Vols2&3); 2019-04-02: Red Draft (Vols2&3) Review Comments due to Victoria 0900; Red Recovery/ Gold Team Kickoff Conference Call (1100); 2019-04-05: Review Gold Draft (Vols1-3); 2019-04-08: Gold Review Comments due to Victoria 0900; Conference Call (1100)
XYZ | SME/Writer #6 | 2019-03-13: Read RFP; gather Q's; 2019-03-22: Review Pink Draft (Vol2); 2019-03-25: Pink Draft (Vol2) Review Comments due to Victoria 0900; Pink Recover/ Red Team Kickoff Conference Call (1100); 2019-03-27: SME Work Session 0900 ACLC Onsite or Call-in (Phase-In/Establish & Recruit/Fluctuating Workloads & Schedules); 2019-03-28: SME Work Session 0900 ACLC Onsite or Call-in (Org Chart/Team Complemen/Labor Mix; Technical Understanding); 2019-04-01: Review Red Draft (Vols2&3); 2019-04-02: Red Draft (Vols2&3) Review Comments due to Victoria 0900; Red Recovery/ Gold Team Kickoff Conference Call (1100); 2019-04-05: Review Gold Draft (Vols1-3); 2019-04-08: Gold Review Comments due to Victoria 0900; Conference Call (1100)
XYZ | SME/Reviewer #1 | 2019-03-13: Read RFP; gather Q's; 2019-03-19: SME Work Session 0900 ACLC Onsite or Call-in (Org Chart/Team Complemen/Labor Mix; Technical Understanding); 2019-03-22: Review Pink Draft (Vol2); 2019-03-25: Pink Draft (Vol2) Review Comments due to Victoria 0900; Pink Recover/ Red Team Kickoff Conference Call (1100); 2019-03-28: SME Work Session 0900 ACLC Onsite or Call-in (Org Chart/Team Complemen/Labor Mix; Technical Understanding); 2019-04-01: Review Red Draft (Vols2&3); 2019-04-02: Red Draft (Vols2&3) Review Comments due to Victoria 0900; Red Recovery/ Gold Team Kickoff Conference Call (1100); 2019-04-05: Review Gold Draft (Vols1-3); 2019-04-08: Gold Review Comments due to Victoria 0900; Conference Call (1100); 2019-04-11: White Glove Review (ACLC On-Site); 2019-04-12: White Glove
XYZ | SME/Reviewer #2 | 2019-03-13: Read RFP; gather Q's; 2019-03-18: SME Work Session 0900 ACLC Onsite or Call-in (Phase-In/Establish & Recruit/Fluctuating Workloads & Schedules); 2019-03-19: SME Work Session 0900 ACLC Onsite or Call-in (Org Chart/Team Complemen/Labor Mix; Technical Understanding); 2019-03-22: Review Pink Draft (Vol2); 2019-03-25: Pink Draft (Vol2) Review Comments due to Victoria 0900; Pink Recover/ Red Team Kickoff Conference Call (1100); 2019-03-27: SME Work Session 0900 ACLC Onsite or Call-in (Phase-In/Establish & Recruit/Fluctuating Workloads & Schedules); 2019-03-28: SME Work Session 0900 ACLC Onsite or Call-in (Org Chart/Team Complemen/Labor Mix; Technical Understanding); 2019-04-01: Review Red Draft (Vols2&3); 2019-04-02: Red Draft (Vols2&3) Review Comments due to Victoria 0900; Red Recovery/ Gold Team Kickoff Conference Call (1100); 2019-04-05: Review Gold Draft (Vols1-3); 2019-04-08: Gold Review Comments due to Victoria 0900; Conference Call (1100); 2019-04-11: White Glove Review (ACLC On-Site)
XYZ | Reviewer #4 | 2019-03-13: Read RFP; 2019-03-22: Review Pink Draft (Vol2); 2019-03-25: Pink Draft (Vol2) Review Comments due to Victoria 0900; Pink Recover/ Red Team Kickoff Conference Call (1100); 2019-04-01: Review Red Draft (Vols2&3); 2019-04-02: Red Draft (Vols2&3) Review Comments due to Victoria 0900; Red Recovery/ Gold Team Kickoff Conference Call (1100); 2019-04-05: Review Gold Draft (Vols1-3); 2019-04-08: Gold Review Comments due to Victoria 0900; Conference Call (1100)
XYZ | Pricing | 2019-03-13: Read RFP; gather Q's; 2019-03-19: SME Work Session 0900 ACLC Onsite or Call-in (Org Chart/Team Complemen/Labor Mix; Technical Understanding); 2019-03-22: Review Pink Draft (Vol2); 2019-03-25: Pink Draft (Vol2) Review Comments due to Victoria 0900; Pink Recover/ Red Team Kickoff Conference Call (1100); 2019-03-28: SME Work Session 0900 ACLC Onsite or Call-in (Org Chart/Team Complemen/Labor Mix; Technical Understanding); 2019-04-01: Review Red Draft (Vols2&3); 2019-04-02: Red Draft (Vols2&3) Review Comments due to Victoria 0900; Red Recovery/ Gold Team Kickoff Conference Call (1100); 2019-04-05: Review Gold Draft (Vols1-3); 2019-04-08: Gold Review Comments due to Victoria 0900; Conference Call (1100); 2019-04-11: White Glove Review (ACLC On-Site)
XYZ | Pricing | 2019-03-13: Read RFP; gather Q's; 2019-03-25: Pink Draft (Vol2) Review Comments due to Victoria 0900; Pink Recover/ Red Team Kickoff Conference Call (1100); 2019-03-28: SME Work Session 0900 ACLC Onsite or Call-in (Pricing)
XYZ | Graphics